## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
2 | Jyoti Kumari | 2026-10-16 | Protected backend APIs were returning an authentication configuration error because the required Supabase JWT configuration was not available in the backend process. | Sprint 3 | Jyoti Kumari | Standards | Configured the backend JWT authentication mode, Supabase JWKS URL, issuer, audience and allowed signing algorithm through the backend environment. | 2026-10-16 | Closed | Backend authentication configuration was loaded successfully and the API moved to token validation.
3 | Jyoti Kumari | 2026-10-16 | The protected API was returning 401 Unauthorized because the JWT verification logic expected RSA keys while the Supabase token used ES256 with an EC key. | Sprint 3 | Jyoti Kumari | Logical | Updated the JWKS verification logic to support EC public keys for ES256 tokens while retaining RSA handling for applicable algorithms. | 2026-10-16 | Closed | Supabase JWKS was verified as EC/P-256 with ES256 and the public key was successfully converted using PyJWT.
4 | Jyoti Kumari | 2026-10-16 | The backend authentication module was missing the current_user dependency required by the existing FastAPI routes. | Sprint 3 | Jyoti Kumari | Logical | Restored the current_user dependency and connected it with the existing token verification function. | 2026-10-16 | Closed | Backend application started successfully without changing the existing authentication architecture.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others